## Slide 1: HTS Expansion at Pfizer: Integrated Automated Lab Systems
HighRes Biosolutions Exhibitor Tutorial, SLAS2026
February 10th, 2026
Rich Frisbie
On Behalf of the HTS Laboratory,
Part of Medicinal Sciences – Discovery Biology & Pharmacology
Pfizer Inc., Groton CT USA.

## Slide 2
Discovery Biology & Pharmacology (DBP) –
High Throughput Screening (HTS) Team
Rich Frisbie
Automation / Data
Jacob Bunch
Automation Engineer
Lucy Stevens
A. Development / Data
Tony Chow
Automation / Data
Jeremy Schriener
Automation / Data
Sarah Hyde
Data Analytics
Joe DiStefano
Contractor
Eric Johnson
HTS Lab Head

## Slide 3: Key Infrastructure & Design Considerations For HTS System Builds
Today’s focus is on build of 3 new HighRes Systems in support of HTS
Leverage new technologies
Faster, more efficient screening
Build our screening capacity
Goal state of the art instrumentation & robotic automation:
Breadth of assay formats (technology, complexity)
  Evaluation of prior Pfizer HTS screens
  1536-well formats
Integration with existing equipment
Redundancy on common workflows
Modular design to enable flexibility
Flexibility to pivot to emerging technologies
EHS compliant
Location of space/feasibility
  Infrastructure to support system and future expansion

## Slide 4: Key Deliverables & Timelines to HTS Build
Jan 2025
Jul
Apr
Jan 2026
Jul
Concepts and Design started back in early 2024
Quote to install, ~10 months
Production, 1-2 weeks post SAT
Design HTS
System(s), Z-Cell + Flex Cart
S1 2024
S2 2024
S1 2025
S2 2025
S1 2026
Z-Cell / TRI-DOC Production
Lab
Renovations
Design HTS HCS System
Installation/SAT of Z-Cell
Installation/SAT of TRI-DOC/Flex Cart
HighRes FAT
(Z-Cell)
HighRes FAT (Flex Cart)
HighRes FAT (HCS) System
Installation/SAT HCS
Full Production Screening
(All 3 systems)
Design TRI-DOC

## Slide 5: 3 New Automated Systems – Lab Space
Existing Automation Space
Tissue Culture
Tissue Culture
Office Suite
Atrium Windows
A-Cell Rail HTS System
(Imaging, Cell-based)
TRI-DOC – Flex Cart
(Plate Reformat, Biochemical)
Z-Cell HTS System
(Biochemical, Cell-Based)

## Slide 6: Z-Cell HTS Screening System: Flexibility
HEPA Enclosure
Cell-based work
Dock Configuration

## Slide 7
TRI-DOC – Assay Plate Reformat/Biochemical HTS​
Echo Flex Cart
EnVision Nexus Cart
Tempest
HighRes Prime
Gantry (Storage)
CERTUS Flex
PicoServe
Dock Configuration
Flex Cart – Reach Envelope
Microspin
XPeel
Plateloc (gas-purge)
Configuration
Limits (Dock 2)

## Slide 8
A-Cell Rail (Imaging) HTS System
Dock Configuration
HEPA Enclosure
Formulatrix Tempest
Chemical Exhaust (PFA) Enclosure
EL406 washer
Dockable Positions
Phenix Imagers or as appreciate
Fixed Table
AmbiStore
XPeel
Plateloc
Liconic Automated Incubators (2)
Heating/cooling
Fixed Table
Echo
Mutidrop Combi (2)
A-Cell Rail (1.5M)

## Slide 9: 3 System Build – Lessons Learned
DO NOT under-estimate the time commitment – facilities, architects, HTS vendors.
  Weight, height, future expansion
Engagement with EHS early and often.
  System requirements (HEPA enclosures, chemical exhaust).
  Safety/Risk Assessments.
FAT/SAT protocol design – this will make or break when production starts.
  Work with HighRes on protocol design, labware, etc.
Integration of older existing equipment with new systems
Camera equipment needs, remote connections (RDC, Net Support).
  After hrs monitoring, error recovery.
  Data/cloud integration (network and workflows).
HighRes cart – parking locations.
New workflow requirements – speak up!
  PFA venting
  Metal lids for cell-based work.
PEOPLE! It takes a village – vendors, architects, building managers, movers, floor scanners, electricians, contractors, IT/digital, EHS, the list goes on-and-on!

## Slide 10: The Team / Acknowledgements
ATCM Liquid Store
Digital
Travis Mathewson
Ryan Arnold
Francisco Roman
Benjamin Rumrill
Janice Palmer
Greg Owens
Christine Guiliano
James Villano
Facilities & Team
Joanne Bautista
Michael Whittaker
Blake Schembri
Bobbi Barber
Kenneth Nicholson
Sam Collazo
Grodsky – Louis Malerba & Team
Dinto Electrical – Jim Clabby, Jeff Fortier & Team
Carlin Construction – Bill Donovan, James Carlin
TLBA – Chris Strange
HTS Expansion Team
Andrea Weston
Markus Boehm
Shree Khunte
Matt Troutman
Discovery Biology & Pharmacology
Eric Johnson
Rich Frisbie
Tony Chow
Lucy Rogers
Jacob Bunch
Sara Hyde
Jeremy Schreiner
Equipment / HTS Vendors
Formulatrix – Cem Sonmez
Revvity – Jordan Attwood, Hafeez Khan
Lab Machines – Brandan Barry
Agilent – Tom Nicholson
BlueCat
Azenta
QInstruments
Thermo Fisher Scientific
Genedata
ERS
Michelle Salafia
Regis Doyonnas
Paula Loria
Tim Foley
Zane Wenzel
Stephen Noell
Fabien Vincent
Business Engagement
Joe Mongillo
George Hajj
Claire Steppan
Sylvie Sakata
Matt Sammons
Environmental Health & Safety
Eric Watters
Jean Ferris
Timothy Green
Josh Hamm
Brian Munton
Zack Gural
Joe Blethen
HighRes
Drew Glatczak
Michael Smith
Nicholas Holan
Gary Perez
Kevin Moccia
Dachao Kuang
Tony Tesoriero
Nat Fullam
Josh Powers
Chris Erikson
Phil Soucy
Tommy Chhim
John Rodrigues
Dally To